## Sheet1
Defect ID | Summary | Severity | Defect Status | Status Whiteboard | RM Prio | Defect Meeting: 20140416 | Defect Meeting: 20140522 | Defect Meeting: 20140625 | Defect Meeting: 20140815 | Defect Meeting: 20140911 | Defect Meeting: 20141020 | Defect Meeting: 20141118 | Defect Meeting: 20150108 | Defect Meeting: 20150218 | Defect Meeting: 20150318 | Defect Meeting: 20150413
1335 | Performance Monitoring: Display Zero Data not working (SDH Trail) | C Minor | Open
2032 | Clock Problem in Zürich (ZHH) on OSN 7500 | B Major | Open |  |  | Boards for 3500 did't passed test | new SW available |  | Defect Meeting: issue happened again with modified boards boards tested in lab have seen similar behavior as old board version boards send to Huawei -> R&D analysis expected from Huawe | Boards in R&D no failure found! SW wait for the test report Same boards shall be shipped back to Swisscom | R&D could not reproduce the problem in China;Action in Ittigen: verify that the 2Mbit is impacted during phase jump. Why we are not observing Pointer Justifications at SDH level? | no incident since change out of EOW board in 7500; measure for an other week than change back to the old board and reproduce the issue again |  | keep defect open until may, perform long-term test in lab and make final decision on this defect in June | Sync problem occure in Lugano; Config changed from 2MHz -> 2Mbit now node runs stable for some days Tester send to Lugarno
5483 | Event Logs flooded with RMON Notification messages | C Minor | Open | 2015.03: Fixed in U2000 V200R014C60
5493 | User Preferences lost after U2000 Upgrade | D Low/Technical Request | Replied | 2013.03: Fixed in U2000 V2R14 |  |  |  |  | retested in V2R14 | [5 empty] | will be verifiied after LiveNet migration | will be verifiied after LiveNet migration
5551 | Email Alarm Notification / NE Name not complete | C Minor | Replied | Fixed: U2000V2R2 |  |  |  |  | retested in V2R14 | [5 empty] | to be tested by Michel Müller
5566 | RM: Configure WDM_OADM / OSN-550 NEs appear in Resource Division submenue | C Minor | Open | 2012:07:Fixed in U2000V2R15C50 |  |  |  |  | to be tested in Lab
5603 | NE-ID missing in Email Notification | D Low/Technical Request | Replied | Fixed in V2R14C60 |  | update needed | OK
5662 | RM: Attribute of existing SNCP not changeable | C Minor | Open | Fixed in: V2R15C50 |  | to be discussed, Torsten to check whether the switching based on SD and xxx are promised Huawei scheint dafür nichts liefern zu wollen. Dann benötigen eben eine Funktion mit der Services nach SNCP Flag gefiltert werden können. Gibt’s derzeit auch nicht. Ohne eigenes Script wären etliche SDH Services ohne SD Flag konfiguriert. | Requirement to have filter criterya for SNCP attributes |  | Huawei to update status of RM | Swisscom request to modify the GUI in order to understand the configuration setting during modification of SNCP connections |  |  |  |  | Huawei to check RM; Swisscom requested that user can search for SNCP switching criteria's
5667 | TR_LOC Alarm EFT8A causes Eth Line down | B Major | Replied | 2013.04 Fixed in: V100R010C03SPC203+SPH207 |  | to be decided whether to introduce patch in ngSDH and then to be verified |  |  | currently no plan to introduce this patch |  |  |  |  | TR_LOC alarm solved in patch release; no coincident with Ethernet trail down
5672 | RM: Board type "Find Object" for "Transfers NE Performance Collection And Export" missing | E Change Request | Replied | Fixed in: U2000V2R14C50 |  |  | no update | [7 empty] | to be tested | to be tested
5673 | RM: ELOM: LPT configuration only board wide configurable | B Major | Replied | Fixed iin V1R6C10 |  |  |  | Why didn't the defect din't got fixed; Fix required | Feature must be implemented in COMP mode, STND mode is not usable in Sonate Network |  |  | Huawei to update defect with release information | no update today | Fixed in V1R6C10; to be confirmed | fix in V1R6C10 confirmed by Huawei
5716 | GNE_MGR_LIMIT_OVER alarm | C Minor | Replied | Fixed: V2R14C50 |  |  | proposal not accepted by SC | Proposal delivered to Daniel Näf -> Workaround can be accepted? |  | a new procedure is required which works in the current and following releases | to be tested |  |  |  | to be tested | to be tested
5776 | Loopback on OSN500 doesn't work with FE Service with no client link | C Minor | Replied | 2013.10: Fixed in V100R002C01SPC306 |  |  |  |  | SC: verify Fix
5811 | AFEC Different AFEC modes cannot be distinguished | C Minor | Replied | Fixed in: V1R10C10 | [10 empty] | Test failed: Swisscom asked to handle this in a general way for all boards not only for some.
5827 | EFT8 card does not discharge FCS errored frames | C Minor | Open | 10.2014: fixed in U2000 V200R014C50 + V1R10C03SPC220 |  | Stefan will adapt operational procedure as workaround |  | fixed in U2000 V200R014C50 + V1R10C03SPC220
5833 | ngWDM: board software not available on NE | B Major | Replied | Fixed in: V1R8C10 | [10 empty] | to be tested | to be tested
5847 | SNCP SDH Trail Creation / SNCP-N not default (SD Attribute) | E Change Request | Open | Fixed in V2R14C50 |  |  | filter requirede duplicate 5662 | Huawei to attache email, open RM for GUI modification. Switching critaria shall be checked in gray coloures | Huawei: to update state
5875 | Functions missing after Login | C Minor | Replied | Fixed in V1R9C00CP3011 |  |  | according Huawei this issue is fixed in CP3002 | not fixed | fixed in V2R14 to be verified |  |  |  |  | verified by operations in live network after introduction of V2R14 | to be verified after live net migration | to be verified after live net migration
5880 | RM: U2000 Task Management / Suspend-Resume Schedule Activation for more tasks in one step missing | E Change Request | Replied | Fixed in V2R15C50 |  |  | expecting feedback and release date from Huawei
5886 | RM: Query network wide M40/VA/OAU values / save actual values to file not possible | E Change Request | Replied | demo in february 2015 | 3 |  | Assign Release and date | RM opend to save optical configuration parameter in CSV file | function is integrated into opt. Doctor, solution to be presented during opt. doctor demo | Target of opt. Doctor demo by end of 2014 | The issue occures only once, due to SCC problems. Swisscom ask's to generate a file with all configured optical values in the network. |  | Demo of AMS requested; this tools is able to deliver the requested values | AMS tool demo week 9 2015 WP: D.Näf; R. Wurth, M.Müller | AMS tool demo week 9 2015 WP: D.Näf; R. Wurth, M.Müller | AMS tool demo week 9 2015 WP: D.Näf; R. Wurth, M.Müller
5909 | After client login Data server processes occupy more than 20% CPU for several minutes / Performance during this time frame not acceptable | C Minor | Replied | Fixed in U2000 V2R14 |  | to be tested in live network |  |  | to be tested with V2R14 | [5 empty] | to be verified after live net migration | to be verified after live net migration
5922 | RM: 96 us transmission delay change over LOG link, causing a PTP phase sync error of 48 us. | B Major | Replied | fixed in V1R8C10 | [10 empty] | test ongoing | to be tested
5924 | TOM ODU1 loopback direction wrong in trail maintenance function | C Minor | Open | [5 empty] | status Huawei |  |  |  |  | Tom Board is OK new patch version required to fix an additional problem at NS2 | update from Huawei expected
5928 | U2000 Session frozen | C Minor | Replied | Observation in V2R14C50 |  |  |  |  | to be disscussed with Huawei R&D expert |  | Observation in V2R14C50 |  |  | to be verified by operations after introduction of V2R14 | to be verified by operations after introduction of V2R14 | to be verified by operations after introduction of V2R14
5931 | SDH Port Creation / Port Selection wrong in Port is directly selected on Access Card | C Minor | Replied | Fixed in V2R14C50CP2011 | [10 empty] | to be tested | to be tested
5935 | Window size not suitable, scrollbar missing | C Minor | Replied | Fixed in: U2000V100R009C00SPC301 | [10 empty] | to be tested | to be tested
5947 | RM: U2000 Operation LOG / Detailed Information about OLP Switch missing | D Low/Technical Request | Replied | Fixed in V2R16C50 |  |  |  |  | to be disscussed with Huawei R&D expert |  | Huawei track as feature request | no feedback from vendor; issue has high importance for Swisscom operations; Swisscom demands an improvement in this area | Swisscom request an earlier release date | new target release V2R15C60 not confirmed yet | to be confirmed
5951 | Configure ODU-2 between cards( 55NO2 ) without clients not possible. | C Minor | Replied | Fixed in V2R14 |  |  | SC requires a fix for this issue | Demo in lab to show the behaviour, attache e-mail | Huawei to attache Workaround to the defekt |  | solution provided, tested in V2R14 implementation to be configured in live network |  |  |  |  | to be tested
5952 | Feature Request: ODU-k Loopback | C Minor | Replied | Fixed in V2R14C50SPCx | 1 |  |  | Assign target release | [7 empty] | to be tested
5954 | RM: ELOM line ports not different configurable. | B Major | Replied | Fixed in OSN1800 V1R6C10 | 2 |  |  |  | SC: both NNI ports of the ELOM board has to be set in differen port modes to be able for interop. With different services and boards swisscom used in Sonate Network |  |  | Huawei to update defect with software version information | Huawi to clarify the situation and update status of the defect | Fixed in V1R6C10; to be confirmed | Fixed confirmed
5958 | RM: Physical Board Information / Query for "Board Bar Code" Information (which contains real the serial number) not possible | E Change Request | Replied | V2R15C50 | 3 |  |  |  | open RM for change request
5961 | WDM Trailsearch / Explanation about duration of trailsearch | C Minor | Replied | V2R14 |  |  |  |  | to be disscussed with Huawei R&D expert |  | to be discussed with Wang Jin Lan | behaviour shall be explaint by Wang Jin Lan to Daniel Näf and Michel Müller | Discussion has been taken place todo: Daniel Näf to update with the decission taken |  | Huawei to answer the question; give us numbers how long the trail search for large network will take and which are the expectations | Huawei to answer the question; give us numbers how long the trail search for large network will take and which are the expectations
5979 | Reset Network Wide Optical Reference values should be restricted to admin user | E Change Request | Open | [7 empty] | modify that the admin user group should be restricted to min. amount of users -> test in V2R14 |  |  |  | a propt shall occure, warning the user of the danger of this operation | solution presented to be attached to the defect and release to be assigned
5983 | Migration Procedure (Move NEs out from Optical container) not fulfilles Swisscom requirement. | C Minor | Replied | Test in V2R14 | [11 empty] | to be verifed after migration to V2R14
5984 | OSN550 no overhead monitoring for lower order connection on SDH boards | C Minor | Replied | Fixed in OSN550 V1R7C20
5985 | RM: Modul Ports (e.g. N1OUO8) show no active alarms | C Minor | Replied | Fixed in V2R15C60 | [5 empty] | Huawei to track this request as feature request; Swisscom requests that alarms have to be maped onto it's origion
5986 | NE Upload / Detailed Log Missing | E Change Request | Replied | Tested in V2R14 | [5 empty] | Discussed with R&D support |  |  |  |  | to be tested | to be tested
5988 | Wrong ODU0 and ODU1 information in the Select The Included Server Trail window for OCh over OSN6800 | B Major | Open | 2014.12: Fixed in U2000 V200R014C50SPC201 | [5 empty] | Huawei announced improvements of the routing algorithm for V2R14CPxy. Huawei to name release and date and explan the proposed fix |  | ODU0 rooting algorithm is getting improved in December patch release; to be retestet during regression testing |  |  | to be tested | test with ODU0 failed
5989 | RM: F2LDGF2: LPT configuration only board wide configurable | B Major | Open | Fixed in V2R15C60 | [5 empty] | Huawei to investigate whether the request can be fullfilled in the COMP mode of the board |  | Huawei to update this defect with release informations | no progress | new target release V2R15C60 not confirmed yet | confirmed V2R15C60
5990 | OSN-8800 T16 / FAN seems not reachable but no NE alarm reported / Ethernet communication SCC towards Boards not observed | C Minor | Replied | Fixed in V1R8C10SPC200 | [10 empty] | to be tested | to be tested
5992 | UC6: Not possible to set constrain at ODU0 level on some sections | B Major | Open | 2014.12: Fixed in U2000 V200R014C50SPC201 | [5 empty] | linked to TR5988 ODU0 routing algorithm problem |  | V200R014C50SPC20112; typo in release information? Huawei to confirm the correct target release |  |  | test ongoing | test with ODU0 failed
5993 | Confusing PopUp window following Cancel (route) Analysis | C Minor | Open | Also failed in V2R14 | [9 empty] | to be retested within V2R14 ODU0 configuration performance | test ongoing | test with ODU0 failed
5994 | Warming Alarm of unknown origin | B Major | Replied | Fixed: U2000V2R14C50SPC201 Dec14 | [5 empty] | Swisscom demands a fix for the problem. Huawei to assign date and release |  |  |  |  | to be tested | to be tested
5997 | Board Version Maintenance / BOM Code missing | C Minor | Replied | [7 empty] | The number of boards is very high. Huawei shall make a proposal, exchange, modify remotely |  | Huawei has changed the policy of BOM code handling; Vladi will verfiy whether the current policy will not be change in the future. |  |  | Huawei to provide a document of the BOM code policy and attach it to the document
5998 | Board Version Maintenance / SW Version wrong / FPGA Version ok | C Minor | Replied | [7 empty] | Swisscom will arrange a maintenance window, Huaweil will modify Board Software version | in progress | Huawei started with the update and continues in the next months |  | cleaning is onging | cleaning is onging
5999 | Board Version Maintenance / SW Version ok / FPGA Version wrong | C Minor | Replied | [7 empty] | Swisscom will arrange a maintenance window, Huaweil will modify FPGA version | in progress | Huawei deliver the correct SW/FPGA versions; Swisscom to exclude passive cards from testlist |  | cleaning is onging | cleaning is onging
6001 | LPT not properly propagated to OSN550-EFS8 on 10 M Eth links | B Major | Replied | 2015.02: Fixed in OSN550 V1R7C30 | [5 empty] | Huawei confirmed that the problem is reproducible
6003 | Board Version Maintenance / SW Version wrong / FPGA Version wrong | C Minor | Replied | [7 empty] | Swisscom will arrange a maintenance window, Huaweil will modify FPGA version | in progress | Swisscom to update boards to the correct board sw version |  | cleaning is onging | cleaning is onging
6006 | Location information of LOOP_ALM wrong on OSN7500 EFT8 | B Major | Replied | Fixed in V2R14C50CP2012 | [5 empty] | problem reproduce able at Huawei, please provide date and release of fix |  | Huawei to update defect with release information |  |  | fix will be included in Hotpatch end of March | to be tested
6007 | Location information of LOOP_ALM wrong on OSN3500 EFT8 | B Major | Replied | Fixed in V2R14C50CP2012 | [5 empty] | problem reproduce able at Huawei, please provide date and release of fix |  | Huawei to update defect with release information |  |  | fix will be included in Hotpatch end of March | to be tested
6011 | Fault loop alarm on EFT cards in the OSN3500 and 7500 | C Minor | Replied | [6 empty] | link to 6006/6007 problem reproduce able at Huawei, please provide date and release of fix |  |  |  |  | to be tested | to be tested
6015 | missing IN/OUT-port when creating DCC-channels on LOG-card | C Minor | Replied | Fixed in V2R15C50
6017 | uflight_dispatcher crashed | C Minor | Replied | [11 empty] | no conclusion by R&D further observation in V2R14 after live net migration | no conclusion by R&D further observation in V2R14 after live net migration
6020 | EFT8 OSN-1500 / LPT not working | C Minor | Replied | V2R14 | [6 empty] | to be reproduced in lab |  |  |  | to be tested | to be tested
6021 | Automated U2000 Inventory Dump not fulfilles expectation | E Change Request | Replied | Fixed in V2R14C50 | [6 empty] | Huawei is verifying if the actual data are taken from NE or from NMS |  |  | Not fixed V2R14; Data not actual they have to be uploaded from NE to NMS; SC asks that the function will be enriched with a function that a NE querry will be performed; AMS may can help us this will be included into the demo | part of AMS demo | part of AMS demo
6030 | WDM Group Protection Report / Information about active selected Channel missing | E Change Request | Replied | Fixed in : V2R15C60
6032 | Errored or missing information in Common Manufacturer Information | C Minor | Replied | 2015.03: Fixed in OSN1800 V1R5C20 | [8 empty] | Swisscom will start to test V1R5C10 version and will may introduce C20 at a later date of V2R14 project. Huawei shall infrom Swissscom as soon as the patch is available | Huawei: give detailed release plan for C20; Swisscom may use it if it will be available bevor April
6034 | RM: F2LSX inband communication down at inital configuration | D Low/Technical Request | Replied | [8 empty] | according documentation client port shall be 10Gbit LAN by default, today it's OTU2 Swisscom demands a fix in the next release | Huawei to update release information; Expected target Release must be V1R5C20 | Huawei put the client mode to OTU2 by default; Doc. Is wrong. Swisscom insists that the default mode shall be 10G Ethernet; change to RM | Swisscom request to change the initial working mode of the F2LSX to 10Gbe | Frank to confirm whether Fastlog can set the client mode to 10Gbe in Thun
6035 | GCC12 issue on 55NO2 board interworking with F2ELOM | C Minor | Replied | 2014.11: Fixed in ngWDM V100R009C10SPC100 | [8 empty] | fixed in current SW version
6037 | Optical Power Management / Create Template which is also accessible for other U2000 Users not possible (global template) | D Low/Technical Request | Replied | Fixed in : V2R15C60
6041 | Database configuration optimize guide | C Minor | Open | [11 empty] | Daniel Näf to provide input
6043 | GCC12 issue on OTU2 NNI of OSN1800 | C Minor | Replied | [9 empty] | Jean-Daniel to update defect |  | Huawei to give infromations why two different GCC framing mode is used | Swisscom decission: does not need GCC12 at the moment inband communication with GCC0 is sufficient close defect; no FPGA upgrade
6045 | NBI Config Tool: Display Problem | C Minor | Replied | Fixed in: V2R15C50 | [7 empty] | Workaround use Internet Explorer |  |  | workaround available
6048 | CORBA: getRouteAndTopologicalLinks error | C Minor | Replied
6049 | High Load of Inventory Process causes Bad Performance | B Major | Replied | fixed in V2R14C50CP2011 | [8 empty] | target in next NMS release | to be verifyed in live network after migration | to be verified after live net migration
6050 | UC2a Not possible to have 2 CPE connected over one OSN6800 shelf | B Major | Replied | 2014.12: Fixed in U2000 V200R014C50SPC201 | [10 empty] | test ongoing
6055 | Windows of U2000 V2R14 application displayed outside of main Window. | B Major | Replied | Fixed in V2R14C50PC2011 | [8 empty] | to be tested |  | Eric will take care of this issue
6056 | RM: OTN Alarming Location Information misleading | C Minor | Replied | [9 empty] | change to RM and forward to Hermann Gysel
6057 | RM: OTN Line board termination port naming misleading | C Minor | Replied | [9 empty] | change to RM and forward to Hermann Gysel
6059 | RM: Web LCT for SDH Equipment | E Change Request | Open | [9 empty] | change to RM and forward to Hermann Gysel |  |  | defect to be keept open until official release is availabel for OSN500/550
6060 | In ngSDH, "Refresh Alarm Status of All Trails" must be limited to admin user. | C Minor | Replied | 2015.03: Fixed in U2000 V200R014C60
6063 | Alarms on ODUk termination points without traffic | B Major | Replied | Fixed in: V1R8C10SPH301 | [8 empty] | solution will be delivered with hotpacht; Huawei to update release infromations |  | to be testet | to be tested
6068 | TN15LSC cold reset measurement set is malfunctioning | B Major | Replied | Fixed in : V1R8C10SPH301 | [8 empty] | Hot patch will resolve this issue Huawei will assign release information |  | to be testet | set to be fixed
6070 | Creating Virtual Fiber takes much too long | B Major | Replied | Fixed in V2R14C50CP2011 | [8 empty] | to be retested with V2R50 in Live Network check; Huawei confirmed as bug, Swisscom request a bugfix in V2R14C50 and R9 |  | to be verified after live net migration | to be verified after live network migration
6072 | TN15LTX T-SFP+ failure during wavelenght modification | C Minor | Replied | [11 empty] | Huawei to check how the modified modules can be shipped to Swisscom | SFP+ modules requires new firmware. Huawei to deliver this modules to swisscom
6073 | TN15LTXT NNI interface has wrong polarity | C Minor | Replied | [9 empty] | Swisscom request a modification of the board bevor field delivery |  | to be accepted as restriction
6076 | Cron disabled after U2000V2R14C50SPC201 patch installation | C Minor | Replied | Fixed in: U2000 V2R14C60 | [10 empty] | accepted for the roll out, resolved in the next release
6079 | Diiffer Board Type with same BOM Code (BOM Code retrieved from BAR Code confirm Huawei instruction) | C Minor | Open | [11 empty] | Vladi has to confirm with supply chain that a single unique numbering scheme has to be applied for all equipments and baords
6080 | Board Data of AUX Cards OSN-3500 (at about 270 cards) missing | C Minor | Replied | [11 empty] | Huawei has to make sure that such boards must not be delivered to customer any more | Swisscom accept and close this issue
6081 | FC800 service not working on 15LTX card | B Major | Replied | Fixed in V1R8C10SPH301 | [10 empty] | to be testet | to be tested
6082 | RM: no FC RMON counters on TN15LTX card | C Minor | Open | [11 empty] | change to an RM; Swisscom to check RMON counters on other boards | according Huawei this is a hardware restriction and cannot be implemented
6085 | Same Boardtype with different Naming (additional Item missing) | C Minor | Replied | [11 empty] | Huawei has to make sure that such boards must not be delivered to customer any more | to be accepted by Swisscom
6087 | U2000 Client Display Problem (webrender, Solaris) | B Major | Replied | Fixed in: V2R14C50CP2012 | [10 empty] | fixed in end of march release | to be tested
6088 | NE OSN-1800 not visible in the ECC management after connect to OSN-6800 | B Major | Replied | Fixed in V1R8C10SPH301 | [10 empty] | the number of adjacent NEs can be configured by command line, this will be included in NE hotpatch the number of allowed adjacent NEs is tested by Hauwei and will be notified to Swisscom and value updated in live network by Huawei
6093 | Fibers may disappear between F2ELOM and 15LTX | C Minor | Replied | [11 empty] | keep open until end of test | keep it open untile V2R14 is released
6094 | GCC0 doesn't work between F2ELOM and 15LTX | B Major | Replied | operations/planning to be notified | [10 empty] | operation to be notified of this restriction | hw restriction
6095 | Button not visible in SDH Trail Management Window | C Minor | Replied | [12 empty] | to be tested
6096 | A manually started "Test GNE" doesn't work properly. | C Minor | Replied | [12 empty] | Swisscom to provide update
6098 | Detailed Analyse of defective 100G card | C Minor | Replied
6099 | browse ethernet performance selecting wrong port (TN15LTX / OTU2) | C Minor | Open | fixed in CP2012 | [10 empty] | fixed in end of march release | to be retested
6101 | RM: NE Feature License management | E Change Request | Open | [12 empty] | keep it open untile V2R14 is released
6104 | WDM Service Authority Management | C Minor | Replied | [12 empty] | keep it open untile V2R14 is released
6105 | RM: MCA boards visible in WDM Signal Flow Diagram | E Change Request | Replied | [12 empty] | Huawei refuced RM due to performance issues; MDS6630 can perform this issue test pending
6109 | Traffic on 15LTX can be interrupted by changing the Port Working Mode | C Minor | Replied | fixed in CP2012 | [11 empty] | to be verified
6110 | short service interruption on FC400 during 3800 upgrade R8 / LOM problems | B Major | Replied | [12 empty] | could not be observed any more defect to be closed
6113 | New discrete WDM Service after U2000 Patch installation V200R014C50CP2011 | C Minor | Replied | [11 empty] | verified in next live network check | keep the defect open until live network upgrade and close after succsessful upgrade
6114 | Loop icon still visible in NE Panel view after automatic clearance | C Minor | Replied | [12 empty] | Swisscom to accept
6115 | RM: optical value shall be configurable in WDM Signal Flow Diagram | E Change Request | Open | [12 empty] | Huawei refused RM due to performance issues; MDS6630 can perform this issue test pending
6116 | graphical display in trail maintenance and loopback function not updated | C Minor | Replied | fixed in CP2012 | [11 empty] | if the loopback mark issue is fixed the update issue can be accepted
6117 | Database restore not working U2000V2R14CP2011 | B Major | Replied | [12 empty] | fixed in current patch
6118 | Not possible to start Database and U2000 anymore | B Major | Replied | [12 empty] | timeout issue not included in last patch Huawei to add workaround in defect
6119 | WDM: Restriction of NE-ID Change not acceptable | B Major | Replied | [11 empty] | Swisscom request a procedure/tool to change the NE-ID, without interrupting traffic and services; | tool is working but tool has to be official lie zed by Huawei first; Huawei to commit a date for the official tool
6121 | RMON Performance may block Client terminals | C Minor | Replied | fixed in CP2012 | [10 empty] | fixed in march release | to be verified
6122 | U2000 Full System Backup and Recovery not working | B Major | Open | [12 empty] | according Huawei fixed Daniel Näf to follow up
6124 | No OCh, OTU4, ODU4 and client alarms when 15LSC board is removed | B Major | Open | [12 empty] | Huawei to analyse whether BD_Status alarm is correlated to path alarm or consequent action
6125 | Comment in Board Manufaturer Information doesn't show it's a tunable SFP | C Minor | Replied | [12 empty] | Swisscom recommend that only the type of SFP module is written to the BMI code. No detailed information about the selectet channel
6126 | Frequency of tunable SFP is only set on initialization of TN15LTX61 board | C Minor | Replied
6127 | RM:Automatic U2000 Operation Log Export / OP Log entries partly not written in one line | C Minor | Replied | [12 empty] | Swisscom expects that now Carrige Returns in CSV files to automatically process this log files by scripts -> Change Request
6128 | Automatic U2000 Operation Log Export / Field names missing (empty line instead) | C Minor | Replied | [12 empty] | correction requested and verfiy whether it's a general issue
6129 | Missing underlying alarms in an already opened Current Alarm window. | C Minor | Open | [12 empty] | if the alarm window is open and new alarms occure they will not be automatically correlated to the alarm window; WA clos and open window again
6130 | OCh cannot be created if endpoints in the same shelf | B Major | Open | [12 empty] | Swisscom expects that Och and OTU2 can be created automatecally between boards in the same shelf
6131 | ODU0 configuration between two OSN-1800 (F2LDGF) not possible (OSN-6800 involved) | B Major | Replied | [12 empty] | ODU0 will be discussed in a separate meeting -> at the moment rolout of ODU1 stoped in live network
6133 | Initialize Database takes too long | B Major | Open | [12 empty] | investigation going on Initiaization of DB works but takes very long Rollout not endanged because this is not a regular job Swisscom expects a better performance
6134 | Service_Outage alarm ist not clearing on 10GE WDM client trail | C Minor | Open
6135 | Export of Board Inventory Data failed | C Minor | Replied | [12 empty] | problem not allways reproducable keep open until next defect meeting
6136 | AUX Board wrong power consumption value in U2000 | D Low/Technical Request | Replied | Fixed in NE V1R9C10
6137 | Traffic flow enabled on 15LSC despite no path configured in NMS | C Minor | Open | [12 empty] | WA: switch off laser, deactivate ODUk Service